## Defect Tracking Log
DEFECT TRACKING LOG
Project Name | MyBazar.com
Program Manager
Project Manager
Purpose: To ensure that the work product meets specifications for performance, defects must be tracked and fixed. These defects may arise from any Phase, but the majority will arise in the Testing Phase and must be properly captured and tracked through resolution. This form will allow documentation of test defects that must be corrected prior to project completion. Also, this form makes it easier to monitor status of the defect correction progress. This form may be used by any member of the software development team.
< Hover by the red triangle in the top left corner for more detail. Use the Instructions on the next tab to fill out fields.>
Defect No. | Date Created | Created By | Defect Description | PM Process | Lifecycle Phase | Priority | Owner | Assigned Date | Estimated Time to Fix | Status | Resolution | Resolution Date | Actual Time to Fix | Root Cause | Status | Priority | PM | Lifecycle Phase
1 | 07.01.2025. | GR26 | 1. Open web browser (e.g. Google Chrome). 2. Open www.mybazar.com web page on web browser. 3. Homepage is displayed. 4. Navigate to any product listing page. 5. Locate the sorting dropdown menu. 6. Select any sorting option (e.g. price ascending, price descending, latest). 7. Products remain in the same order - sorting has no effect. EXPECTED RESULT: Products should be reordered according to the selected sorting option. | [6 empty] | New |  |  |  |  | New
2 | 07.01.2025. | GR26 | 1. Open web browser (e.g. Google Chrome). 2. Open www.mybazar.com web page on web browser. 3. Homepage is displayed. 4. User is logged in. 5. Navigate to any product page. 6. Click on the 'Add to Wishlist' button (heart icon). 7. Navigate to the Wishlist page. 8. The product is not displayed in the Wishlist. EXPECTED RESULT: The product should be displayed in the user's Wishlist. | [6 empty] | New |  |  |  |  | Under Review | High | Opportunity Assessment | Opportunity Assessment
3 | 07.01.2025. | GR26 | 1. Open web browser (e.g. Google Chrome). 2. Open www.mybazar.com web page on web browser. 3. Homepage is displayed. 4. Navigate to the 'Latest' page or scroll down on homepage. 5. Locate the tags section at the bottom. 6. Click on the 'tshirt' tag. 7. An empty page is displayed with no products. EXPECTED RESULT: Empty tags should not be displayed to users. | [6 empty] | New |  |  |  |  | In Progress | Medium | Initiating | Concept
4 | 07.01.2025. | GR26 | 1. Open web browser (e.g. Google Chrome). 2. Open www.mybazar.com web page on web browser. 3. Homepage is displayed. 4. Hover over the 'Djeca' category in the navigation menu. 5. Click on the first subcategory 'Rano učenje'. 6. An empty category page is displayed with no products. EXPECTED RESULT: Empty categories should not be displayed in the navigation menu. | [6 empty] | New |  |  |  |  | Completed | Low | Planning | Requirements
5 | 07.01.2025. | GR26 | 1. Open web browser (e.g. Google Chrome). 2. Open www.mybazar.com web page on web browser. 3. Homepage is displayed. 4. Locate the search bar. 5. Enter special characters "@#$%^&" in the search field. 6. Press Enter or click the search button. 7. HTTP 400 error page is displayed. EXPECTED RESULT: A user-friendly message should be displayed instead of HTTP error code. | [6 empty] | New
Note on E10: ====== ID#AAAAn_rmfi0 Julie Arnold (2023-01-09 19:26:29) Choose from the drop down box.
Note on F10: ====== ID#AAAAn_rmfiw John Casey (2023-01-09 19:26:29) Choose from the drop down box.
Note on G10: ====== ID#AAAAn_rmfio Julie Arnold (2023-01-09 19:26:29) Choose from the drop down list
Note on K10: ====== ID#AAAAn_rmfis Julie Arnold (2023-01-09 19:26:29) Choose from the drop down list.

## Defect Tracking Log Instruc
Defect Tracking Log Instructions
Field | Description
Defect Number | Unique identifier for the defect, i.e., 1,2 etc.
Date Created | Date on which the defect was initially reported and logged.
Created By | Name of the person who reported the defect.
Defect Description | Description of the defect. State the subsystem, area, or other part of the product in which the defect occurs or which is affected by the defect.
PM Process | Choose the Project Management Process this defect was reported for: Opportunity Assessment, Initiating, Planning, Executing/Controlling and Closing.
Lifecycle Phase | List the lifecycle this defect was reported for. The Software Development lifecycle is: Opportunity Assessment, Concept, Requirements, Design, Development, Testing, Documentation and Training, Deployment and Post Deployment.
Priority | The priority code indicates the impact of this defect on the project:
H = High (extremely important, the project cannot be successful without this defect being resolved)
M = Medium (important to project success, but a work around exists)
L = Low (desirable, but with little impact to project success if the defect is not resolved)
Owner | Name of the person who is responsible for fixing the defect.
Assigned Date | Date on which the defect was assigned for resolution.
Estimated Time To Fix | Estimated amount of time required to correct the defect. If applicable list in hours, not days.
Status | Current status of the defect: New, In Progress, Under Review and Completed.
Resolution | Description of the defect’s resolution.
Resolution Date | Date on which the defect is to be resolved (or is resolved depending upon its status).
Actual Time to Fix | Actual time required to correct the defect.
Root Cause Description | State the cause of the defect (for example, communication, oversight, transcription, education, process, bad code.).